## Tasks
Triforcia July Internship P2P Car Rental App Tasks
| Issue | Priority | Story Points | Description
Setup
1 | Create Object and Fields | 1 | 1 | Please refer the powerpoint presentation, Fill all description and help texts
2 | Create a Lightning App | 1 | 1 | Name: P2P Car Rental Tabs: Objects created+ Account, Contact, Opportunity, Lead Profile: System Administrator
3 | Create 3 profile and permission sets | 1 | 0.5 | Manager. Refer the powerpoint for details
4 | Create 2 users | 1 | 0.5 | Create 2 user: System Admin and Manager
5 | Create 5 roles | 1 | 0.5 | Car Owner, Car Renter, Manager, Sales, Service
6 | Organization Wide Default Settings | 1 | 0.5 | Please refer the powerpoint presentation
7 | Create a Account record type and page layout for Vehicle owners and Stakeholders | 1 | 0.5 | Create both record type and page layouts and assign
8 | Vehicle owner can lookup on Accounts only if the account is a vehicle owner | 1 | 0.5 | Filter by account record type
11 | Update Page Layouts | 1 | 0.5 | Update Account, Contact and Opportunity Page Layouts to keep related fields to the P2P Car Rental App
12 | Enable Digital Experiences | 1 | 0.5 | Create a experience micro-site and pages for P2P Car Rental App
13 | Create Experience Pages | 1 | 0.5 | Make it user friendly and estethic
14 | Create 2 profiles for Experience Pages | 1 | 0.5 | Clone Customer Community Plus User; 1 profile for Car Owner, 1 profile for , Car Renter (Assign related permission sets)
Automation
1 | Automatically update Last Odometer reading, Odometer Reading date of Vehicle records based on last created Vehicle Renting record | 2 | 3 | Consider add additional relationship and you may need to ensure correct vehicle record will be updated Hint: Trigger
2 | Automatically update inUse field to set "true" if vehicle assigned to keyless records | 2 | 3 | Update InUse after creation and update (cover both scenario: Add vehicle or remove vehicle) Hint: Trigger
3 | Start Date field on the Rental Listing will be today's date automatically | 1 | 1 | Follow best practices for finding a solution. Coding or Point and click tools?
4 | Automatically update isActive field on the Rental Listing records | 1 | 1 | If current date is between start date and end date, set true; if not set false
5 | If Vehicle Owner opt-in for Smart price, set Is smart price field true and price field will be unavailable automatically on Rental Listing | 2 | 3 | Hint: Trigger for is Smart Price and error on price field if is Smart Price true
6 | Update Renting Type automatically on Vehicle Renting based on the Rate Type on Rental Listing | 1 | 1 | Consider deleting the renting type field and add again with another field type
7 | Calculate renting amount automatically for Vehicle renting records | 1 | 1 | Calculate by Renting type and Renting duration. Consider deleting the field and add again with another field type.
8 | Calculate Snapp Car Fee for Vehicle renting records automatically based on Renting amount | 1 | 1 | Snap Car fee is 20%. Consider deleting the field and add again with another field type.
9 | Calculate insurance fee automatically for Vehicle renting records | 1 | 1 | Insurance fee 10% of the renting amount. minimum insurance fee can be less than $ 5. Consider deleting the field and add again with another field type.
10 | Show surcharge fee automatically for Vehicle renting records if the Vehicle older than 15 years. | 1 | 1 | Surcharge fee is %25. Consider deleting the field and add again with another field type.
11 | Show young driver fee for renters less than 25 years old for Vehicle renting records | 1 | 1 | Young Driver fee is %25. Consider deleting the field and add again with another field type.
12 | Add One-off verification fee for contacts if their first rent on the platform for Vehicle renting records. | 1 | 1 | One-off verification fee is $15. Consider adding fields on contact and vehicle renting.
13 | Calculate extra mile fee for Vehicle renting records | 1 | 1 | Extra mile fee should be $0 if it is less than mile allowance on the rental listing
14 | Calculate roadside assistance fee for Vehicle renting records | 1 | 1 | $2 daily. For hourly renting, it should be $2 total.
15 | Calculate final amount automatically for Vehicle renting records | 1 | 1 | Tax included for all fee, apply long term discount 15% if vehicle owner opt-in
16 | VIN is required Vehicle | 1 | 0.5 | Validation or Required field? Discuss and decide
17 | Duplication rule for Contact, Account and Vehicle | 1 | 0.5 | Records can not be created if Name and Email or Phone are the same
18 | Throw an error for Vehicle renting if Vehicle is not active or already rented | 2 | 3 | (Hint: Trigger)
19 | Send an email to vehicle owners once their rental listing is created and contacts once their vehicle renting created. | 2 | 3 | Please refer the powerpoint presentation for the email template
20 | Create Unit test classes for Apex coding | 2 | 7 | For Triggers and Apex Classes. Please refer the powerpoint presentation
21 | Rental Listings should be inactive if end date is older than current date. | 3 | 2 | Is active should be automatically false if listing end date is yesterday (at 12 am everyday) Hint: Schedule Apex
22 | Update Rental Listing Title automatically | 3 | 3 | Rent + Vehicle Name + Rent Type : for example: "Rent Tesla Model Y Daily "
23 | Deactivate all vehicles and rental listings automatically once Vehicle owner is not active | 2 | 2 | Hint: Trigger
24 | Automatically delete all old Rental Listing records first Sundayof every month | 3 | 3 | Automatically delete all records if it is older than 12 months. Notify admin user via email about the result Hint: Batch Apex
25 | Calculate the total earning amount of vehicle renting for Rental Listings automatically | 1 | 1 | Calculate total earnings for the rental listing, exlcuding all fees
26 | Update isKeyless field for Vehicle Renting records if a keyless assigned to the vehicle | 2 | 5 | Hint : Update current Trigger, do not create another one!
Client Interface
1 | Create a form to register as a car renter | 3 | 3 | Hint: LWC or Flow
2 | Create a list of available cars to rent | 3 | 1 | Hint: LWC or Flow
3 | Use your insipiration to create an experience cloud page | 3 | 7 | Design a microsite to satisfy this kind of business. Add components and modules as you like.
Optional | Create solution for task 1 & 2 with using other method (LWC or Flow) | 3 | 7 | If you created the solution with Flow, try to recreate with LWC or vice versa
Integration
1 | Create Apex REST to send available cars to rent to external system | 1 | 1 | Only active vehicles will be available, Test the REST Api with Postman
Optional | Integrate Docusign for payments | 3 | 3 | Test your integration with sending one document and signed.
Optional | Integrate Stripe for payments | 3 | 5 | Test your integration with creating one flow to create an invoice
Optional | Show a map on home page to show available car locations | 3 | 2 | Show placeholders of isActive=true rental listings on a map, Select Experience Page or App Home Page. Add address field for the rental listing object
Deployment
1 | Use Jira indivudally to track tasks | 1 | 1 | Create 1 sprint for 2 weeks and add target tasks to this sprint. Remaining tasks will be on the backlog.
Optional | Use your GitHub repository and VSCode for the project. Push all metadata to your GitHub repository | 3 | 3 | Test your integration with sending one document and signed.
Optional | Use Devops Center for at least 1 task. | 3 | 7 | Hint: Development environment can be scracth org.
Optional | Create a complete solution package at the end of your project | 3 | 3 | Show placeholders of isActive=true rental listings on a map, Select Experience Page or App Home Page. Add address field for the rental listing object
Optional | Deploy all metadata to another org using manifest file on workbench at the end of your project | 3 | 3 | Show placeholders of isActive=true rental listings on a map, Select Experience Page or App Home Page. Add address field for the rental listing object